## Online Projects with Children
Template Student-Led Project's Risk Assessment for Online Projects with Children
|  | Please note that this risk assessment template does not include the Additional Information tab that you need to complete for your project risk assessment | [6 empty] | Terminology
|  | Please download the complete risk assessment form from the Project Leader Resources webpage | [6 empty] | To avoid confusion use the following terminology throughout the risk assessment
|  | Use the Hazard Checklist tab, included in the risk assessment form, to identify additional hazards for your project | [6 empty] | Participants = the beneficiaries of your project
|  | Remember that you will also need to risk assess the activities that will be delivering during the online workshops. | [6 empty] | Volunteers = the UCL students volunteering with your project
|  | Use a new row for each hazard | [6 empty] | Partner Organisation = the schools/community organisations you are working with
|  | Ensure that you complete the Additional Information tab, this can be found on the risk assessment form | [6 empty] | Safeguarding Lead = partner organisation staff responsible for safeguarding
|  | For projects planning to deliver in-person activity, it is advisable to develop a contingency plan and risk assess this plan so that you can revert to online delivery if needed | [6 empty] | Project Supervisor = Volunteering Service staff who supports you with your project
Please feel free to use any rows from this template, that are relevant to your Student-Led Project, in your project's risk assessment
|  | Project Name:- | Science Club |  |  | Date :- | 2021-10-01
Club/Society Name | Additional Activity | Activity Type | Identify Hazards* | Identify Consequences | Likelihood of Incident Occurring | Severity of Consequence | Risk Rating | Identify Control Measures | Person Responsible | Identify Action if Incident Occurs
|  | Please list the different types of activities you intend to carry out in the academic year | List the potential and real hazards (what has the potential to cause harm) for each activity type | Please list the consequences of each hazard, i.e. what harm, damage or loss may result - and who might be affected (e.g. volunteers or participants) | Rate between 1-5 where 1 is extremely unlikely and 5 is extremely likely | Rate between 1 - 5 where 1 is extremely minor and 5 is extremely serious | This is the likelihood x severity - (please do not edit formula in this column) | Control measures can prevent harm - usually more than one control measure should be used for any given hazard. | Who is responsible for ensuring that control measures are implemented for this activity type (please give name, email, and phone number) | What action will you take if an accident or incident does occur? Please note emergency telephone numbers here.
|  | Workshops with children/ young people | Workshop hacked | Participants experience online abuse | 1 | 5 | 5 | 1) Password protect the meeting 2) Turn on waiting room function of online platform 3) Only share meeting details via email 4) Co-host on hand to act as admin and remove those who gate crash session 5) Use UCL approved platform 6) Safeguarding Lead identified within organisation and contact details shared with volunteers | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Co-host to remove gate crasher from meeting 2) Ensure participants are fine before continuing or end session if required 3) Volunteers referred to UCL Psychological services if required 4) Volunteering Service Incident Report completed 5) Safeguarding Lead informed
|  |  | Inappropriate content shared | Young people watching could be distressed. | 1 | 5 | 5 | 1) Volunteers and Project Leaders to complete Volunteering with Children (VWC) Training 2) Project Leaders to ensure all volunteers have completed VWC Training before they participate in workshops 3) Safeguarding Lead identified within organisation and volunteers informed how to contact them. 4) Expected behaviour outlined at the start of workshop 5) Co-host on and to act as admin 6) Remove the ability to screen share if not required during workshop | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Volunteers told to inform Safeguarding Lead of organisation 2) Safeguarding Lead informed 3) Volunteering Service's Incident Report completed 4) Perpetrator removed from workshop 5) If perpetrator is volunteer, they will be reported to the Volunteering Service and their future with project discussed 6) If the perpetrator is a participant they should be warned initially, if behaviour continues they should be removed from the session and a discussion had with teacher about whether they can continue with project
|  |  | Safeguarding allegation made against a volunteer | Participants experience abuse. | 1 | 5 | 5 | 1) All volunteers to attend Volunteering with Children Training 2) Safeguarding Lead identified within organisation and volunteers informed how to contact them 3)Volunteers complete DBS checks 4) Project Leaders to ensure all volunteers have a clear DBS check and have completed VWC training before they start volunteering 5) Supervisor from partner organisation to be present in all sessions 6) Volunteers informed that there needs to be at least 2 volunteers delivering each session and that if there are not a minimum of 2 volunteers the session has to be cancelled | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Safeguarding Lead informed 2) Volunteers suspended while allegation investigated 3) Volunteering Service Informed 4) Volunteering Service Incident Report completed
|  |  | Safeguarding disclosure made to a volunteer | Volunteer does not know how to report a safeguarding disclosure Participants safeguarding disclosure is not investigated meaning participant is still at risk | 1 | 5 | 5 | 1) All volunteers to attend Volunteering with Children Training 2) Safeguarding Lead identified within organisation and volunteers informed how to contact them | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Safeguarding Lead informed
|  |  | Lack of information, training or instruction/ Poor activity planning or preparation | Poor quality workshop delivered Participants do not benefit from engagement | 1 | 3 | 3 | 1) Provide all volunteers with appropriate training before they commence their roles 2) Obtain feedback from volunteers, so that gaps in knowledge can be identified and further training provided if needed | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) If organisation reports concerns with quality of workshop, observe sessions to ensure volunteers are delivering as planned. 2) If session are being delivered as planned review content 3) If volunteers report that they do not know how to deliver workshops, provide with additional training 4) Review volunteer induction and training programme
|  |  | Lack of hardware/software required | Volunteers/ Participants not able to participate in workshops | 2 | 3 | 6 | 1) Check that volunteers have required equipment and software during recruitment process 2) Maintain regular communication with volunteers to identify any issues with equipment or software and then try to resolve them 3) Communicate with partner organisation to ensure that they have the required hardware and software 4) Obtain budget for software, if required | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Use budget to purchase software required 2) If participants do not have the hardware required to access sessions, provide materials in an alternative format.
|  |  | Computer/laptop battery runs out | Volunteer disconnects from session and session cannot be delivered as planned Not enough volunteers to deliver sessions | 5 | 1 | 5 | 1) Volunteer advised to ensure that their devices are fully charged before session 2) Volunteers advised to be near a power source and have their charger available at all times. 3) All volunteers to be confident to deliver all sections of the workshop | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Another volunteer to take over hosting until the volunteer returns to session 2) If there is only 1 volunteer remaining on the call, the session to be ended if the volunteer does not return
|  |  | Unsafe behaviour or attitude | Participants exposed to unsafe behaviours or attitudes | 1 | 3 | 3 | 1) All volunteers will be required to complete the Volunteering with Children online course. 2) Safeguarding Lead contact details obtained and shared with volunteers. 3) Expected behaviour outlined at the start of session 4) Supervisor from partner organisation to be present in all sessions | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) If Volunteer displays this behaviour/attitude then they will removed from workshop and suspended from taking part in the rest of the programme until an investigation is concluded. 2) Incident report completed immediately. 3) Volunteers referred to UCL Psychological Services if required. 4) Ensure all participants and Volunteers are okay to continue the session. 5) Safeguarding lead notified regardless of Volunteer or participant portraying the unsafe behaviour/attitude. 5) If participant is portraying the unsafe behaviour/attitude then teacher will deal with the participant 6) Project Leaders to discuss the participants involvement in future sessions
|  |  | Non-UCL students participating in workshops | Participants put at risk because these students have not been DBS checked | 1 | 2 | 2 | 1) Only share meeting links to UCL email addresses 2) Use UCL approved platforms 3) Inform volunteers that they must only use their UCL email address to join sessions 4) Inform non-UCL students that they cannot volunteer with the project 5) Safeguarding Lead contact details obtained and shared with volunteers. | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Inform non-UCL students that they are unable to volunteer with project 2) Volunteering Service Incident Report completed. 3) Safeguarding Lead Informed if required
|  |  | Software inaccessible for people with disabilities | Participants with disabilities unable to access session | 3 | 3 | 9 | 1) Discuss any accessibility needs with teacher before sessions start 2) Make sure accessibility features of software are turned on, if required. 2) If software is not accessible, acquire a suitable alternative. 4) Liaise directly with the partner organization to find a suitable alternative | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) If software is found to be inaccessible during session, discuss other alternatives with partner organisation 2) Discuss funding for software with Project Supervisor if needed 3) Provide workshop content in an alternative format if disabled participants are unable to access the session
|  |  | Volunteer connects with participant on social media | Inappropriate relationship between participant and volunteer outside scheduled volunteer sessions | 2 | 3 | 6 | 1) Volunteers and Project Leaders to complete Volunteering with Children (VWC) Training 2) Project Leaders to ensure all volunteers have completed VWC Training before they participate in workshops 3) Safeguarding Lead identified and volunteers informed how to contact them. | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Safeguarding Lead informed 2) Volunteers suspended while allegation investigated 3) Volunteering Service Informed 4) Volunteering Service Incident Report completed
|  |  | Inappropriate comments made on chat | Participants experience online abuse | 2 | 3 | 6 | 1) Volunteers and Project Leaders, to complete Volunteering with Children (VWC) Training 2) Project Leaders to ensure all volunteers have completed VWC Training before they participate in workshops 3) Safeguarding Lead identified and volunteers informed how to contact them. 4) Outline expected behaviours at the start of sessions 5) Disable private chat function | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Safeguarding Lead informed 2) If volunteer makes the inappropriate comment depending on severity they will be removed from session 3) Volunteers suspended while allegation investigated 4) Volunteering Service Informed 5) Volunteering Service Incident Report completed 6) If participant makes inappropriate comment a warning is given and if behaviour continues remove them from session 7) Discuss participants removal with teacher
|  |  | School/Organisation closed because of Covid-19 | Participants are not able to meet with their team to work on their project | 2 | 1 | 2 | 1) Maintain regular communication with organisation so that Project Leaders are informed if school has to close because of Covid-19 2) Produce and risk assess contingency plan, so that participants can login from home | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Put contingency plan in place and run session with participants logging in from home 2) Postpone sessions and reschedule when schools reopen.
|  |  | Ignorance of rules and / or procedures | Volunteers do not know how to safeguard the participants online Participants experience online abuse | 3 | 5 | 15 | 1) Volunteers and Project Leaders to complete Volunteering with Children (VWC) Training 2) Project Leaders to ensure all volunteers have completed VWC Training before they participate in workshops 3) Safeguarding Lead identified and volunteers informed how to contact them. | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Safeguarding Lead informed 2) Volunteers suspended while allegation investigated 3) Volunteering Service Informed 4) Volunteering Service Incident Report completed
|  |  | Lack of skill | Poor quality workshop delivered Participants do not benefit from engagement | 2 | 2 | 4 | 1) Provide all volunteers with appropriate training before they commence their roles 2) Obtain feedback from volunteers and provide further training if needed | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) If organisation reports concerns with quality of workshop, observe sessions to ensure volunteers are delivering as planned. 2) If session are being delivered as planned review content 3) If volunteers reports that they do not know how to deliver workshops, provide with additional training 4) Review volunteer induction and training programme
|  |  | Poor internet connection | Session disrupted | 3 | 2 | 6 | 1) During recruitment ask interested UCL students about their internet connection and speak to Project Supervisor about possible solutions if it is poor. If solution cannot be found try identifying other ways the volunteer can be involved in project 2) Sessions will be run by at least 3 volunteers so that even if one volunteer loses internet access the session will be continued by other volunteers. 3) Ensure that volunteers are able to deliver all parts of the workshop | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Other volunteers to take over delivery of session until volunteer returns 2) Volunteers to inform Project Leaders. 3) Project Leader to adapt future sessions to cover any material that couldn't be covered or provide content in an alternative format 4) If a volunteer has a recurring problem with internet connection, discuss possible solutions with Project Supervisor. If it cannot be resolved, try and identify other ways the volunteer can be involved in the project
|  |  | Volunteer unwell | Not enough volunteers available to deliver workshop because a minimum of 2 volunteers is required | 5 | 2 | 10 | 1) Have minimum of 3 volunteers scheduled to facilitate each workshop 2) Ensure all volunteers are made the host of all sessions, so that any volunteers can be a backup if required 3) All volunteers to be trained on all parts of the workshops so that they can step in as a back up if needed 4) Inform volunteers that they need to let the Project Leaders know as soon as possible if they are unable to attend a workshop 5) Volunteers informed that there needs to be at least 2 volunteers delivering each session and that if there are not a minimum of 2 volunteers the session has to be cancelled | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Volunteers to cancel session if there are not at least two volunteers present 2) Project Leaders to contact school to reschedule session or provide content in an alternative format 3) If volunteer did not notify the volunteers in advance, volunteers reminded to call in sick 4) If session went ahead with only 1 volunteer, volunteers reminded that there needs to be at least 2 volunteers delivering each session for it to go ahead
|  |  | Having access to participants personal contact details | Volunteer connect with participant outside of sessions | 3 | 3 | 9 | 1) Zoom sessions to be created by partner organisation where possible and volunteers made co-hosts 2) All Volunteers are required to take the Volunteering with Children Training before any activity takes place. 3) The Safeguarding Lead's details are obtained before hand. 4) To minimise the number of people having access to the participants' personal email addresses, only 1 Project Leader will create the Zoom meeting. The other Project Leaders will be made a co-host. The Project Leader who created the meeting will not share the personal details generated from the attendance lists with anyone else. | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) The Safeguarding Lead is informed immediately 2) Volunteering Service Incident Report is completed. 3) Volunteer suspended while allegation investigated 4) All future Zoom meetings to be created by the school
|  |  | Volunteer connecting to session from a public space or with other people present | Confidential information overheard and disclosed to others | 3 | 3 | 9 | 1) Volunteers told to ensure that they volunteer in a private space with no one else present and to wear headphones where possible 2) Volunteers provided with a code of conduct | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Volunteer reminded to follow the code of conduct 2) Volunteer Incident Report completed 3) Partner Organisation informed if confidential information about participant is shared
0

## In-Person Projects for Children
Template Student-Led Project's Risk Assessment for In-Person Projects with Children
|  | Please note that this risk assessment template does not include the Additional Information tab that you need to complete for your project risk assessment | [6 empty] | Terminology
|  | Please download the complete risk assessment form from the Project Leader Resources webpage | [6 empty] | To avoid confusion use the following terminology throughout the risk assessment
|  | Use the Hazard Checklist tab, included in the risk assessment form, to identify additional hazards for your project | [6 empty] | Participants = the beneficiaries of your project
|  | Do not forget to risk assess tne different activities that your participants and volunteers will be participating in | [6 empty] | Volunteers = the UCL students volunteering with your project
|  | Use a new row for each hazard | [6 empty] | Partner Organisation = the schools/community organisations you are working with
|  | Ensure that you complete the Additional Information tab, this can be found on the risk assessment form | [6 empty] | Safeguarding Lead = partner organisation staff responsible for safeguarding
|  | For projects planning to deliver in-person activity, it is advisable to develop a contingency plan and risk assess this plan so that you can revert to online delivery if needed | [6 empty] | Project Supervisor = Volunteering Service staff who supports you with your project
Please feel free to use any rows from this template, that are relevant to your Student-Led Project, in your project's risk assessment
|  | Project Name:- | Science Club |  |  | Date :- | 2021-10-01
Club/Society Name | Additional Activity | Activity Type | Identify Hazards* | Identify Consequences | Likelihood of Incident Occurring | Severity of Consequence | Risk Rating | Identify Control Measures | Person Responsible | Identify Action if Incident Occurs
|  | Please list the different types of activities you intend to carry out in the academic year | List the potential and real hazards (what has the potential to cause harm) for each activity type | Please list the consequences of each hazard, i.e. what harm, damage or loss may result - and who might be affected (e.g. volunteers or participants) | Rate between 1-5 where 1 is extremely unlikely and 5 is extremely likely | Rate between 1 - 5 where 1 is extremely minor and 5 is extremely serious | This is the likelihood x severity - (please do not edit formula in this column) | Control measures can prevent harm - usually more than one control measure should be used for any given hazard. | Who is responsible for ensuring that control measures are implemented for this activity type (please give name, email, and phone number) | What action will you take if an accident or incident does occur? Please note emergency telephone numbers here.
|  | Workshops with Children | Inappropriate content shared on presentation slides | Young people could be distressed. | 1 | 5 | 5 | 1) Volunteers and Project Leaders to complete Volunteering with Children (VWC) Training 2) Project Leaders to ensure all volunteers have completed VWC Training before they participate in workshops 3) Safeguarding Lead identified within organisation and volunteers informed how to contact them. 4) Project Leaders to approve content before it is shared with participants | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Volunteers told to inform Safeguarding Lead of organisation 2) Safeguarding Lead informed 3) Incident reported to Project Supervisor 4) Volunteering Service's Incident Report completed 4) Volunteer who developed content identified and either provided with additional training or removed from the project
|  |  | Safeguarding allegation made against a volunteer | Participants experience abuse. | 1 | 5 | 5 | 1) All volunteers to attend Volunteering with Children Training 2) Safeguarding Lead identified within organisation and volunteers informed how to contact them 3)Volunteers complete DBS checks 4) Project Leaders to ensure all volunteers have a clear DBS check and have completed VWC training before they start volunteering 5) At least two volunteers to be present during every session | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Safeguarding Lead informed 2) Volunteers suspended while allegation investigated 3) Volunteering Service Informed 4) Volunteering Service Incident Report completed
|  |  | Safeguarding disclosure made to a volunteer | Volunteer does not know how to report a safeguarding disclosure Participants safeguarding disclosure is not investigated meeting participant is still at risk | 1 | 5 | 5 | 1) All volunteers to attend Volunteering with Children Training 2) Safeguarding Lead identified with organisation and volunteers informed how to contact them | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Safeguarding Lead informed
|  |  | Lack of information, training or instruction/ Poor activity planning or preparation | Poor quality workshop delivered Participants do not benefit from engagement | 1 | 3 | 3 | 1) Provide all volunteers with appropriate training before they commence their roles 2) Obtain feedback from volunteers, so that gaps in knowledge can be identified and further training provided if needed | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) If organisation reports concerns with quality of workshop, observe sessions to ensure volunteers are delivering as planned. 2) If session are being delivered as planned review content 3) If volunteers reports that they do not know how to deliver workshops, provide with additional training 4) Review volunteer induction and training programme
|  |  | Unsafe behaviour or attitude/ Poor behaviour | Participants exposed to unsafe behaviours or attitudes | 1 | 3 | 3 | 1) All volunteers will be required to take the Volunteering with Children online course. 2) Safeguarding Lead contact details obtained and shared with volunteers. 3) Expected behaviour outlined at the start of session 4) Supervisor from partner organisation to be present in all sessions | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Volunteering Service Incident report completed. 2) Safeguarding lead notified 3) Project Leaders to discuss the perpetrators involvement in future sessions with Project Supervisor and partner organisation
|  |  | Non-UCL students participating in workshops | Participants put at risk because these students have not be DBS checked | 1 | 2 | 2 | 1) Ensure that all volunteers are registered with SLP webpage before they start volunteering 2) Inform non-UCL students that they cannot volunteer with the project | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Inform non-UCL students that they are unable to volunteer with project 2) Volunteering Service Incident Report completed.
|  |  | School/Organisation closed because of Covid-19 | Participants are not able to meet with their team to work on their project | 2 | 1 | 2 | 1) Maintain regular communication with organisation so that Project Leaders are informed if school has to close because of Covid-19 2) Produce and risk assess contingency plan, so that participants can login from home | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Put contingency plan in place and run session with participants logging in from home 2) Postpone sessions and reschedule when schools reopen.
|  |  | Ignorance of rules and / or procedures | Volunteers do not know how to safeguard the participants Participants experience abuse | 3 | 5 | 15 | 1) Volunteers and Project Leaders to complete Volunteering with Children (VWC) Training 2) Project Leaders to ensure all volunteers have completed VWC Training before they participate in workshops 3) Safeguarding Lead identified and volunteers informed how to contact them. | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Safeguarding Lead informed 2) Volunteers suspended while allegation investigated 3) Volunteering Service Informed 4) Volunteering Service Incident Report completed
|  |  | Lack of skill | Poor quality workshop delivered Participants do not benefit from engagement | 2 | 2 | 4 | 1) Provide all volunteers with appropriate training before they commence their roles 2) Obtain feedback from volunteers and provide further training if needed | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) If organisation reports concerns with quality of workshop, observe sessions to ensure volunteers are delivering as planned. 2) If session are being delivered as planned review content 3) If volunteers reports that they do not know how to deliver workshops, provide with additional training 4) Review volunteer induction and training programme
|  |  | Volunteer unwell | Not enough volunteers available to deliver workshop | 5 | 2 | 10 | 1) Have additional volunteers scheduled to facilitate each workshop, if needed 2) All volunteers to be trained on all parts of the workshops so that they can step in as a back up if needed 3) Inform volunteers that they need to let the Project Leaders know as soon as possible if they are unable to attend a workshop | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Project Leaders to cancel session if there are not at least two volunteers available to deliver session 2) Project Leaders to contact school to reschedule session or provide content in an alternative format 3) If volunteer did not notify the volunteers in advance, volunteers reminded to call in sick
|  |  | Insufficient or unsuitable space | Participants unable to participate safely | 3 | 3 | 9 | 1) Organisation informed of the type of space needed prior to workshop 2) Send reminder email detailing the type of space needed | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Deliver alternative activities 2) Cancel the session if it cannot be delivered safely 3) Review communication with partner organisation to see whether this needs to be improved 4)Reminder partner organisation about type of space needed for next session
|  |  | Untidiness (trip / fire hazard) Slip / trip / fall hazards | Participant or volunteers trips and hurts themselves | 3 | 3 | 9 | 1) Volunteers briefed on health & safety and informed to ensure that trip hazards are removed immediately. 2) Provide participants with safety instructions 3) Procedures for alerting first aider provided to volunteers prior to session taking place 4) Ensure that volunteers are made aware of the fire evacuation procedures | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) First aider alerted and 999 called if required 2) Follow schools evacuation procedures if fire occurs 3) Project Supervisor informed 4) Volunteering Service Incident report completed
|  |  | Fire | Participant or volunteer injured in fire | 1 | 5 | 5 | 1) Ensure that volunteers are made aware of the fire evacuation procedures | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) 999 called, if needed 2) Follow schools evacuation procedures if fire occurs 3) Project Supervisor informed 4) Volunteering Service Incident report completed
|  |  | Allergies | Participant suffers allergic reaction | 1 | 5 | 5 | 1) Supervising teacher to be present 2) Potential allergens highlighted and sent to school prior to session 3) Procedures for alerting first aider provided to volunteers prior to session taking place 4) Allergies checked with teacher present before session | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) First aider alerted and 999 called if required 2) Project Supervisor informed 3) Volunteering Service Incident report completed
|  |  | Covid-19 or transmissible diseases | Participant or volunteers becomes unwell | 3 | 3 | 9 | 1) Volunteers will be informed not to attend sessions if they are displaying any covid symptoms. 2) Volunteers will wash their hands on arrival. 3) Windows will be opened so room is well ventilated. 4) Register taken and all volunteer details kept for 14 days after actvity. 5) Ask partner organisation about local control measures that should be followed | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Volunteer to follow current national and UCL reporting guidelines 2) Project Leaders to inform partner organisation if volunteer recently attended session 3) Project Supervisor to be informed 4) Project to be moved online if needed

## Sheet1 (hidden)
Compliant with no new controls
Compliant with new controls
Not currently compliant
New activity in response to Covid-19

## Pre-recorded sessions
Template Student-Led Project's Risk Assessment for Pre-Recorded Sessions
|  | Please note that this risk assessment template does not include the Additional Information tab that you need to complete for your project risk assessment | [6 empty] | Terminology
|  | Please download the complete risk assessment form from the Project Leader Resources webpage | [6 empty] | To avoid confusion use the following terminology throughout the risk assessment
|  | Use the Hazard Checklist tab, included in the risk assessment form, to identify additional hazards for your project | [6 empty] | Participants = the beneficiaries of your project
|  | Use a new row for each hazard | [6 empty] | Volunteers = the UCL students volunteering with your project
|  | Remember that you will also need to risk assess the activities that will be included in the pre-recorded sessions | [6 empty] | Partner Organisation = the schools/community organisations you are working with
|  | Ensure that you complete the Additional Information tab, this can be found on the risk assessment form | [6 empty] | Safeguarding Lead = partner organisation staff responsible for safeguarding
|  | For projects planning to deliver in-person activity, it is advisable to develop a contingency plan and risk assess this plan so that you can revert to online delivery if needed | [6 empty] | Project Supervisor = Volunteering Service staff who supports you with your project
Please feel free to use any rows from this template, that are relevant to your Student-Led Project, in your project's risk assessment
|  | Project Name:- | Science Club |  |  | Date :- | 01/10/2021
Club/Society Name | Additional Activity | Activity Type | Identify Hazards* | Identify Consequences | Likelihood of Incident Occurring | Severity of Consequence | Risk Rating | Identify Control Measures | Person Responsible | Identify Action if Incident Occurs
|  | Please list the different types of activities you intend to carry out in the academic year | List the potential and real hazards (what has the potential to cause harm) for each activity type | Please list the consequences of each hazard, i.e. what harm, damage or loss may result - and who might be affected (e.g. volunteers or participants) | Rate between 1-5 where 1 is extremely unlikely and 5 is extremely likely | Rate between 1 - 5 where 1 is extremely minor and 5 is extremely serious | This is the likelihood x severity - (please do not edit formula in this column) | Control measures can prevent harm - usually more than one control measure should be used for any given hazard. | Who is responsible for ensuring that control measures are implemented for this activity type (please give name, email, and phone number) | What action will you take if an accident or incident does occur? Please note emergency telephone numbers here.
|  | Sending Pre-recorded sessions to Partner Organisation | Computer viruses/ email hacking. | Viruses / email hacking may be experienced by staff or volunteers who download the pre-recorded session and personal data may be lost or hacked. | 2 | 4 | 8 | 1) Scan recordings for viruses before sending to organisation | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Inform organisation about virus as soon as notified about it 2) Complete Volunteering Service's Incident Report
|  | Providing Pre-recorded session for those unable to access live sessions | Lack of hardware/software | Participants unable to access pre-recorded sessions because they do not have a device | 3 | 5 | 15 | 1) Check with Partner Organisation whether participants have device to access recording 2) Identify an accessible way to share pre-recorded sessions | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) If participants complain that they unable to access pre-recorded material, work with partner organisation to identify other ways that participants can access the recordings
|  |  | Participants not engaging with pre-recorded sessions | Not achieving our project aims | 3 | 3 | 9 | 1) Organisations invited to express an interest in pre-recorded sessions 2) Organisation informed that feedback will be sought to find out how the participants found the pre-recorded sessions 3) Obtain feedback from organisations asking whether they used pre-recorded sessions with their participants | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Send Reminder to organisation to complete feedback form 2) Ask for feedback from organisation on how participants can be encouraged to watch recordings
|  | Recording sessions to send to organisation | Covid-19 or transmissible diseases | Volunteers being infected with covid-19 | 2 | 1 | 2 | 1) Volunteers will be informed not to attend recording sessions if they are displaying any covid symptoms. 2) Volunteers will wash their hands on arrival. 3) Windows will be opened so room is well ventilated. 4) Register taken and all volunteer details kept for 14 days after actvity. | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Volunteer to follow current national and UCL reporting guidelines p 2) Project Supervisor informed
|  |  | . Volunteers not participating in producing recording | Participants not receiving pre-recorded sessions | 3 | 4 | 12 | 1) Produce schedule for recording sessions 2) Hold recording sessions at a consistent time | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Remind volunteers of times that recording sessions are taking place 2) Recruit additional volunteers if needed
|  |  | Pre-recorded sessions not produced on time | Organisation not engaged in project and do not send pre-recorded videos to participants | 3 | 4 | 12 | 1) Develop timeline to produce recording 2) Set deadlines for volunteers to submit individual content for the recording 3) Set timetable for online group practise and recording sessions 4) Investigate software needed for editing software so that it can be purchased as soon as it is needed 5) Set a timeline for editing the recording | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Keep organisation informed about any delays in producing pre-recorded session 2) Recruit additional volunteers to produce the recording
|  |  | Lack of recording equipment/editing software | No recordings develop | 1 | 4 | 4 | 1) Research recording and editing software and apps so that these can be purchased as soon as needed 2) Apply for budget to purchase software and apps, 3) Develop a recording and editing timeline and plan in preparation. | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Speak to Project Supervisor if problems arise 2) Notify Partner Organisation if there is a delay in recording sessions
|  |  | Inappropriate Content Shared | Participants exposed to harmful material/ REPUTATIONAL risk to, the Student-Led Project, Union, UCL | 1 | 1 | 1 | 1) Project Leaders to check all performances before sharing them with partner organisations 2) Safeguarding Lead identified with organisation and volunteers informed how to contact them | Project Leaders project.leaders@ucl.ac.uk 01234 567 890 | 1) Report to Volunteering Service 2) Complete Volunteering Service Incident Report 3) Volunteer suspended while investigation conducted 4) Safeguarding Lead Informed 5) Apology sent to organisation 6) Performance approval process reviewed
0
0
0
0
0
0
0
0
0
0
0
0